## Hoja2
STAGE | ACTIVITIES | FEBRUARY | [27 empty] | MARCH | [30 empty] | APRIL
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
Planning | bar: 1 to 2; 5 to 7
Project | bar: 1
Meeting | bar: 2
Lifecycle | bar: 5
Policies | bar: 6
Project Plan | bar: 7
Analysis | bar: 8 to 9; 12
Requeriments management | bar: 8 to 9
Identify requerements suppliers | bar: 8
Define data collection techniques | bar: 8
Identify system processes | bar: 9
Identify functional requirements | bar: 9
Identify non-functional requirements | bar: 12
Manage requriments traceability | bar: 12
Design | bar: 13 to 16; 19 to 23; 26 to 28
UML Diagrams | bar: 13 to 16
Use cases | bar: 13 to 14
Sequence Diagrams | bar: 15 to 16
Class diagrams | bar: 19 to 20
E-R Diagram | bar: 21 to 22
Scketch | bar: 23; 26
Navigation Map | bar: 27 to 28
Develoment | bar: 1 to 2; 5 to 9; 12 to 16; 19 to 22
Encode database | bar: 1
Modules | bar: 1 to 2; 5 to 9; 12 to 16; 19 to 22
Products | bar: 2; 5 to 6
Interface | bar: 2
Register | bar: 2
Delete | bar: 5
Update | bar: 5
List | bar: 6
Gallery | bar: 6 to 8
Interface | bar: 6
Register | bar: 7
List | bar: 7
Delete | bar: 8
Update | bar: 8
Contact | bar: 9; 12
Interface | bar: 9
Register | bar: 9
List | bar: 12
Delete | bar: 12
FAQ | bar: 13 to 15
Interface | bar: 13
Register | bar: 13
List | bar: 14
Delete | bar: 14
Update | bar: 15
News | bar: 15 to 16; 19
Interface | bar: 15
Register | bar: 16
List | bar: 16
Delete | bar: 19
Update | bar: 19
User | bar: 20 to 22
Interface | bar: 20
Register | bar: 20
List | bar: 21
Delete | bar: 21
Update | bar: 22
Test | bar: 22 to 23; 26 to 28
Testing module | bar: 22 to 23; 26
Quality Testing | bar: 26 to 28
End of Proyect | bar: 29 to 30; 2 to 6
Letter of Acceptance | bar: 29 to 30; 2
Proyect closure | bar: 2 to 3
Performance evaluation | bar: 3 to 4
Delivery of documentation and presentation | bar: 4 to 5
Final report | bar: 5 to 6